## Start Here
Stage-Pay Tracker
Build at home from abroad. No proof, no payment.
How it works
1 |  | Fill in the Project tab: your builder's name, location and start date.
2 |  | On the Stages tab, enter the agreed price for each stage. Rename or adjust stages to match your contract.
3 |  | Check the Proof Checklist. Each stage has a list of photos, videos and receipts to ask for. Add or remove items to suit your build.
4 |  | Before paying for a stage, open the WhatsApp tab. It writes the message asking for any missing proof. Copy it and send it to your builder.
5 |  | As proof arrives, set 'Received?' to Yes on the Proof Checklist. Paste a link to where you saved the photo or video.
6 |  | Every time you send money, add a row to the Payments tab. The Dashboard updates by itself.
The rule
• |  | A stage is Verified only when money has been sent AND every proof item is received.
• |  | The next stage stays Locked until the previous one is Verified. Don't send money to a locked stage.
• |  | 'Unproven' on the Dashboard is money you've sent that isn't backed by proof yet. Aim to keep it at $0 before each new payment.
Colour key
Yellow cells: type here
White cells: worked out for you, so don't type over them
Tabs
Dashboard: totals, progress and your next step
Project: your project details
Stages: agreed price, money sent and status for each stage
Payments: every transfer you make
Proof Checklist: what to ask for at each stage, and what you've received
WhatsApp: ready-to-send messages for your builder and family
Before You Build: checks to do first, and red flags to watch for
Using Google Sheets
Upload this file to Google Drive, then open it with Google Sheets (or go to File > Import in a new sheet). Everything works on a phone in the Google Sheets app.
Important
Stage-Pay is a record-keeping tool. It isn't legal, financial or engineering advice, and it can't guarantee how a builder behaves. For large projects, consider an independent inspector or engineer to check the work on site.

## Dashboard
4-room house
Stand 1234, Chitungwiza · Builder: Tendai M.
Total budget | Sent | Verified built | Unproven | Budget left
38900 | 14200 | 11600 | 2600 | 24700
Verified | 29.82% | ████████████
Sent, no proof yet | 6.684% | ███
(Bars show share of total budget)
Where you are now
Current stage | Window level
Status | Hold payment
Next step | Hold. 3 proof item(s) missing. Send the WhatsApp request.
Payment warnings | None
All stages
Stage | Agreed | Sent | Proof | Status
1. Foundation & footings | 5400 | 5400 | 6 of 6 | Verified
2. Slab level (DPC & floor slab) | 6200 | 6200 | 6 of 6 | Verified
3. Window level | 4800 | 2600 | 2 of 5 | Hold payment
4. Roof level (lintels & wall plate) | 3000 | 0 | 0 of 5 | Locked
5. Roofing | 7500 | 0 | 0 of 5 | Locked
6. Plumbing & electrical (first fix) | 2500 | 0 | 0 of 5 | Locked
7. Plaster & ceilings | 3500 | 0 | 0 of 4 | Locked
8. Floors, doors & finishing | 6000 | 0 | 0 of 6 | Locked

## Project
Project details
Fill in the yellow cells.
Project name | 4-room house | e.g. 4-room house
Location / stand number | Stand 1234, Chitungwiza | e.g. Stand 1234, Chitungwiza
Builder name | Tendai M. | Used in your WhatsApp messages
Builder WhatsApp number | +263 77 000 0000
Site contact (family or friend) | Brother: Farai (visits on Saturdays) | Someone you trust who can visit the site
Start date | 2026-03-01
Currency | USD | All amounts in this tracker use this currency

## Stages
Stages
Enter the agreed price for each stage (yellow). Everything else updates from the Payments and Proof Checklist tabs.
# | Stage | Agreed price | Sent | Left to pay | Proof items | Proof received | Proof % | Status | Next step | Open?
1 | Foundation & footings | 5400 | 5400 | 0 | 6 | 6 | 100% | Verified | Done. All proof received. | 0
2 | Slab level (DPC & floor slab) | 6200 | 6200 | 0 | 6 | 6 | 100% | Verified | Done. All proof received. | 0
3 | Window level | 4800 | 2600 | 2200 | 5 | 2 | 40% | Hold payment | Hold. 3 proof item(s) missing. Send the WhatsApp request. | 1
4 | Roof level (lintels & wall plate) | 3000 | 0 | 3000 | 5 | 0 | 0% | Locked | Wait. Don't send money until the previous stage is verified. | 1
5 | Roofing | 7500 | 0 | 7500 | 5 | 0 | 0% | Locked | Wait. Don't send money until the previous stage is verified. | 1
6 | Plumbing & electrical (first fix) | 2500 | 0 | 2500 | 5 | 0 | 0% | Locked | Wait. Don't send money until the previous stage is verified. | 1
7 | Plaster & ceilings | 3500 | 0 | 3500 | 4 | 0 | 0% | Locked | Wait. Don't send money until the previous stage is verified. | 1
8 | Floors, doors & finishing | 6000 | 0 | 6000 | 6 | 0 | 0% | Locked | Wait. Don't send money until the previous stage is verified. | 1
9 |  |  | 0 |  | 0 | 0 | 0% |  |  | 0
10 |  |  | 0 |  | 0 | 0 | 0% |  |  | 0
| Total | 38900 | 14200 | 24700
Rows 9 and 10 are spare. Type a stage name to use them. 'Open?' is a helper column the Dashboard uses.

## Payments
Payments
Add a row every time you send money. Pick the stage number (1–10) the money is for.
Date | Stage # | Stage | Amount | Method | Paid to | What it was for / reference | Check | Total sent
2026-03-04 | 1 | Foundation & footings | 3000 | Mukuru | Tendai M. | Foundation materials | OK | 14200
2026-03-21 | 1 | Foundation & footings | 2400 | Bank transfer | Tendai M. | Foundation labour | OK
2026-04-15 | 2 | Slab level (DPC & floor slab) | 4000 | Mukuru | Tendai M. | Bricks and cement for slab level | OK
2026-05-02 | 2 | Slab level (DPC & floor slab) | 2200 | Bank transfer | Tendai M. | Slab and labour | OK
2026-06-10 | 3 | Window level | 2600 | WorldRemit | Tendai M. | Bricks to window level | OK

## Proof Checklist
Proof Checklist
What to ask for before each stage is paid. Set 'Received?' to Yes when it arrives. Add your own items in the empty rows at the bottom.
Stage # | Stage | Proof to ask for | Received? | Date received | Where it's saved (link or note) | msg
1 | Foundation & footings | Setting-out photo: pegs and strings match the approved plan | Yes | 2026-04-10 | Google Drive > Build > Stage 1
1 | Foundation & footings | Trenches with a tape measure showing depth and width | Yes | 2026-04-11 | Google Drive > Build > Stage 1
1 | Foundation & footings | Footings poured: photo of every trench | Yes | 2026-04-12 | Google Drive > Build > Stage 1
1 | Foundation & footings | Foundation brickwork up to ground level: photo of each side | Yes | 2026-04-13 | Google Drive > Build > Stage 1
1 | Foundation & footings | Video walking round the whole foundation | Yes | 2026-04-14 | Google Drive > Build > Stage 1
1 | Foundation & footings | Receipts: cement, sand, stone, bricks | Yes | 2026-04-15 | Google Drive > Build > Stage 1
2 | Slab level (DPC & floor slab) | Brickwork to slab level: photo of each side | Yes | 2026-05-10 | Google Drive > Build > Stage 2
2 | Slab level (DPC & floor slab) | Damp-proof course (DPC) visible all round | Yes | 2026-05-11 | Google Drive > Build > Stage 2
2 | Slab level (DPC & floor slab) | Hardcore filled and compacted | Yes | 2026-05-12 | Google Drive > Build > Stage 2
2 | Slab level (DPC & floor slab) | Slab poured: photo across the whole floor | Yes | 2026-05-13 | Google Drive > Build > Stage 2
2 | Slab level (DPC & floor slab) | Receipts: cement, mesh, DPC, hardcore | Yes | 2026-05-14 | Google Drive > Build > Stage 2
2 | Slab level (DPC & floor slab) | Council stage inspection signed (if your council requires it) | Yes | 2026-05-15 | Google Drive > Build > Stage 2
3 | Window level | Photo of each outside wall | Yes | 2026-06-10 | Google Drive > Build > Stage 3
3 | Window level | Window frames set in place | Yes | 2026-06-11 | Google Drive > Build > Stage 3
3 | Window level | Door frames set in place | No |  |  | 1
3 | Window level | Video walking through every room | No |  |  | 2
3 | Window level | Receipts: bricks, cement, frames | No |  |  | 3
4 | Roof level (lintels & wall plate) | Lintels over every door and window | No
4 | Roof level (lintels & wall plate) | Ring beam / brickforce at wall plate | No
4 | Roof level (lintels & wall plate) | Walls at full height: photo of each side | No
4 | Roof level (lintels & wall plate) | Video walk-round inside and outside | No
4 | Roof level (lintels & wall plate) | Receipts: steel, cement, bricks | No
5 | Roofing | Trusses up: photo from two corners | No
5 | Roofing | Roof covering complete: photo from the road | No
5 | Roofing | Fascia boards and gutters fitted | No
5 | Roofing | Photo of the roof from inside, before ceilings | No
5 | Roofing | Receipts: timber, sheets/tiles, nails, straps | No
6 | Plumbing & electrical (first fix) | Conduits and boxes in the walls: photo of each room | No
6 | Plumbing & electrical (first fix) | Water pipes and drainage laid | No
6 | Plumbing & electrical (first fix) | Septic tank or sewer connection: photo | No
6 | Plumbing & electrical (first fix) | Name and phone number of the electrician and plumber | No
6 | Plumbing & electrical (first fix) | Receipts: cables, pipes, fittings | No
7 | Plaster & ceilings | Inside plaster done: video of every room | No
7 | Plaster & ceilings | Outside plaster done: photo of each side | No
7 | Plaster & ceilings | Ceilings fitted: photo of each room | No
7 | Plaster & ceilings | Receipts: cement, plaster sand, ceiling boards | No
8 | Floors, doors & finishing | Floor screed or tiles done: video of every room | No
8 | Floors, doors & finishing | Doors hung and locks fitted | No
8 | Floors, doors & finishing | Window glass fitted | No
8 | Floors, doors & finishing | Painting done inside and outside | No
8 | Floors, doors & finishing | Sinks, toilet, lights and switches installed | No
8 | Floors, doors & finishing | Final receipts and handover of keys | No

## WhatsApp
WhatsApp messages
Copy a message, paste it into WhatsApp and send. Your builder's name comes from the Project tab.
| Stage to ask about | 3 | ← Picks your current stage. Type a different number (1–10) to change it.
| Stage name | Window level
Missing proof
| 1 | Door frames set in place
| 2 | Video walking through every room
| 3 | Receipts: bricks, cement, frames
4
5
6
7
8
9
10
Message: ask for missing proof
| Copy the cell on the right → | Hi Tendai M., hope you and the team are well. Before I send the next payment for window level, please send: 1. Door frames set in place 2. Video walking through every room 3. Receipts: bricks, cement, frames Thank you!
More ready-made messages
| Before work starts: agree the rule | Hi Tendai M., before we start, here's how I'll handle payments so we're always clear. For each stage I'll send you a short list of photos, a video and receipts. Once I have them, I send the money for the next stage the same day. It's the same for every stage and everyone I work with. Is that OK with you?
| Proof is late | Hi Tendai M., just checking in on the photos and video for window level. I'm ready to send the next payment as soon as they come through.
| Holding a payment politely | Hi Tendai M., thanks for the update. I'm still missing a few items for window level (see my list above). I'll release the payment as soon as they're in, so we keep to the agreed system.
| Price has gone up | Hi Tendai M., understood. Please send the supplier's quote or receipt showing the new price. Once I see it, I'll update the budget and we can agree the new amount.
| For family managing the site | Hi, thank you so much for keeping an eye on the build, it means a lot. To keep things simple and fair for everyone, I'm using the same system for every stage: photos, a short video and receipts before each payment. Could you help me get these for window level?
| Payment sent | Hi Tendai M., I've sent the payment for window level today. Please confirm when you receive it. Thank you for the good work!

## Before You Build
Before you build
Do these checks before you send the first payment. Mark each one Yes when it's done.
| Check | Done? | Notes
| The stand is legally yours: title deed, or cession / agreement of sale, checked with the Deeds Registry, the council or the developer, in YOUR name | No
| You've seen the stand's beacons (in person, by someone you trust, or on a live video call) | No
| You know what servicing is done (water, sewer, roads) and what it will cost if it isn't | No
| Building plans are approved by the local council before any work starts | No
| You've met the builder (in person or on video) and seen at least 2 houses they've built | No
| You've spoken to at least one past client of the builder | No
| Written agreement signed: what will be built, price per stage, timeline, who buys materials, what happens if work stops | No
| Payment schedule agreed: money per stage, and the next stage paid only after proof | No
| Proof list sent to the builder before work starts (WhatsApp tab, 'Before work starts') | No
| Someone you trust, who isn't the builder, can visit the site now and then | No
| Where possible, you pay material suppliers directly and keep their receipts | No
| One folder (e.g. Google Drive) for all photos, videos, receipts and agreements | No
| Checks done | 0 of 12
Red flags: stop and ask questions if you see these
⚑ Asks for most of the money up front, before any work
⚑ Asks you to send money to a different person or account than you agreed
⚑ Photos are always close-ups, from the same angle, or there's never a video
⚑ Says 'prices went up' but can't show a supplier quote or receipt
⚑ Work has stalled, but requests for money keep coming
⚑ Pressure to pay today: 'the materials will be gone' or 'the price changes tomorrow'
⚑ Becomes hard to reach right after you send a payment
⚑ Seller can't show the stand beacons, or rushes you to pay before you've checked ownership